## Kinara Project Plan
Kinara Capital - Implementation Plan - 2016 | [9 empty] | Gantt For |  |  | Planned |  |  |  |  | Current Week |  |  |  | 9
Week Start --> | [9 empty] | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-04 | 2016-07-11 | 2016-07-18 | 2016-07-25 | 2016-08-01 | 2016-08-08 | 2016-08-15 | 2016-08-22 | 2016-08-29 | 2016-09-05 | 2016-09-12 | 2016-09-19 | 2016-09-26 | 2016-10-03 | 2016-10-10 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19
Phase | Stage ID | Stage | % Completion | Responsibility | Duration | Start Date | End Date | Actual/Expected Start Dt | Actual/Expected End Dt | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Phase I | P1RS001 | Requirements/Process Deep Dive | 100 | IRF | 27 days | 2016-06-06 | 2016-07-12 | 2016-06-13 | 2016-07-29
Phase I | P1RS002 | Requirements Signoff | 100 | Kinara | 28 days | 2016-06-06 | 2016-07-13 | 2016-07-14 | 2016-08-03
Phase I | P1UI001 | UI Design Development | 55 | IRF | 8 days | 2016-08-03 | 2016-08-13 | 2016-08-03 | 2016-08-18
Phase I | P1UI002 | UI Design Sign Off | 0 | Kinara | 2 days | 2016-08-16 | 2016-08-17
Phase I | P1UI003 | UI Design Rework | 0 | IRF | 3 days | 2016-08-17 | 2016-08-19
Phase I | P1TP001 | Test Plan Delivery | 0 | Kinara | 10 days | 2016-07-16 | 2016-07-30 | 2016-08-08 | 2016-08-27
Phase I | P1MG001 | Migration Discussion | 100 | IRF, Kinara | 1 day | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21
Phase I | P1MG002 | Migration Strategy Document | 100 | IRF | 5 days | 2016-07-28 | 2016-08-03 | 2016-07-28 | 2016-08-05
Phase I | P1MG003 | Migration Strategy Document Sign off | 0 | Kinara | 5 days | 2016-08-04 | 2016-08-12 | 2016-08-04 | 2016-08-12
Phase I | P1MG004 | Migration Script Preparation | 0 | IRF | 5 days | 2016-08-16 | 2016-08-20 | 2016-08-16 | 2016-08-20
Phase I | P1CD001 | Customization Delivery | 0 | IRF | 38 days | 2016-07-20 | 2016-08-19 |  | 2016-08-26
Phase I | P1CD002 | UI Integration with Services | 0 | IRF | 7 days | 2016-08-16 | 2016-08-22 | 2016-08-16 | 2016-09-20
Phase I | P1SIT002 | SIT Test Plan | 0 | IRF | 7 days | 2016-08-18 | 2016-08-26 | 2016-08-18 | 2016-08-26
Phase I | P1SIT003 | SIT Test Plan Review | 0 | IRF | 6 days | 2016-08-22 | 2016-08-29 | 2016-08-22 | 2016-08-29
Phase I | P1SIT001 | System Integration Testing | 0 | IRF | 5 days | 2016-08-23 | 2016-08-27 | 2016-08-24 | 2016-09-03
Phase I | P1UT001 | User Training | 0 | IRF | 5 days | 2016-08-22 | 2016-08-27 | 2016-08-29 | 2016-09-03
Phase I | P1UAT001 | UAT Setup | 0 | IRF | 2 days | 2016-08-28 | 2016-08-29 | 2016-08-26 | 2016-08-27
Phase I | P1MG005 | Migration Testing Round 1 | 0 | IRF,Kinara | 5 days | 2016-08-30 | 2016-09-02 | 2016-08-28 | 2016-09-09
Phase I | P1MG006 | Migration Testing Round 2 | 0 | IRF,Kinara | 5 days | 2016-09-05 | 2016-09-09
Phase I | P1MG007 | Migration Sign off | 0 | Kinara | 2 days | 2016-09-12 | 2016-09-13 | 2016-09-12 | 2016-09-13
Phase I | P1MP009 | User Acceptance Testing | 0 | IRF,Kinara | 15 days | 2016-08-30 | 2016-09-17 | 2016-09-05 | 2016-09-28
Phase I | P1MP010 | UAT Sign off | 0 | Kinara | 1 day | 2016-09-24 | 2016-09-24 | 2016-09-29 | 2016-09-29
Phase I | P1MP011 | Go Live | 0 | IRF | 3 days | 2016-09-30 | 2016-10-02
Phase I | P1MP012 | Post Live -Onsite support | 0 | IRF | 2 days | 2016-10-03 | 2016-10-15 | 2016-10-03 | 2016-10-15
Phase II | P2RS001 | Requirements/Process Deep Dive | 0 | IRF | 15 days | 2016-07-21 | 2016-08-10
Phase II | P2RS002 | Requirements Signoff | 0 | Kinara | 5 days | 2016-08-11 | 2016-08-16
Phase II | P2UI001 | UI Design Documents Signoff | 0 | IRF, Kinara | 5 days | 2016-08-17 | 2016-08-23
Phase II | P2TP001 | Test Plan Delivery | 0 | Kinara | 8 days | 2016-08-17 | 2016-08-26
Phase II | P2MG001 | Migration Discussion | 0 | IRF, Kinara | 1 day | 2016-08-29 | 2016-08-29
Phase II | P2MG002 | Migration Strategy Document | 0 | IRF | 4 days | 2016-08-30 | 2016-09-02
Phase II | P2MG003 | Migration Strategy Document Sign off | 0 | Kinara | 3 days | 2016-09-05 | 2016-09-07
Phase II | P2MG004 | Migration Script Preparation | 0 | IRF | 5 days | 2016-09-08 | 2016-09-14
Phase II | P2CD001 | Customization Delivery | 0 | IRF | 35 days | 2016-08-24 | 2016-10-14
Phase II | P2SIT001 | System Integration Testing | 0 | IRF | 5 days | 2016-10-17 | 2016-10-21
Phase II | P2UT001 | User Training | 0 | IRF | 3 days | 2016-10-19 | 2016-10-21
Phase II | P2UAT001 | UAT Setup | 0 | IRF | 2 days | 2016-10-22 | 2016-10-23
Phase II | P2MG005 | Migration Testing Round 1 | 0 | IRF,Kinara | 5 days | 2016-10-24 | 2016-10-28
Phase II | P2MG006 | Migration Testing Round 2 | 0 | IRF,Kinara | 5 days | 2016-10-31 | 2016-11-04
Phase II | P2MG007 | Migration Sign off | 0 | Kinara | 2 days | 2016-11-07 | 2016-11-08
Phase II | P2MP009 | User Acceptance Testing | 0 | IRF,Kinara | 15 days | 2016-11-04 | 2016-11-24
Phase II | P2MP010 | UAT Sign off | 0 | Kinara | 1 day | 2016-11-25 | 2016-11-25
Phase II | P2MP011 | Go Live | 0 | IRF | 3 days | 2016-12-03 | 2016-12-05
Phase II | P2MP012 | Post Live -Onsite support | 0 | IRF | 2 days | 2016-12-06 | 2016-09-07
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
[7 empty] | 2016-08-24 | 2016-08-25 |  | 2016-06-13: 14
[7 empty] | 2016-08-26 | 2016-09-03 |  | 2016-06-13: 14
[7 empty] | 2016-08-26 | 2016-09-03
[7 empty] | 2016-08-29 | 2016-09-03
[7 empty] | 2016-09-05 | 2016-09-28
[7 empty] | 2016-09-29 | 2016-09-29

## Process
Sl.No | Stage ID | Process ID | Process Name | Process Document Link | Scope | Remarks | Status | Pending With | ETA Date | Signoff Date
1 | P1RS001 | RM1001 | Loan Booking | https://drive.google.com/file/d/0ByaFA5DUraUDRTlaMEFvcVJROFU/view?usp=sharing | Phase I | Attached final process map. | Signed Off | - |  | 2016-07-18
2 | P1RS001 | RM1002 | Document Tracking | https://drive.google.com/file/d/0ByaFA5DUraUDTlotRUdKOGo4dms/view?usp=sharing | Phase 2 | Attached final process map. | Signed Off | - |  | 2016-07-18
3 | P1RS001 | RM1003 | Inventory Management | Draft version shared and comments received from Kinara | Phase 2 | This process map will be prepared by Krithika | Signed Off |  |  | 2016-07-28
4 | P1RS001 | RM1004 | Collections | https://drive.google.com/file/d/0ByaFA5DUraUDVDVXOFpITFVZbTQ/view?usp=sharing | Phase I | Attached final process map for Collection and Bounce Resolution | Signed Off | - |  | 2016-07-18
5 | P1RS001 | RM1005 | Customer Notifications | https://drive.google.com/file/d/0ByaFA5DUraUDRWV6N1pjaVpLR1k/view?usp=sharing | Phase I | Kinara shared latest Customer notifications sheet. IRF to review | Signed Off | - |  | 2016-07-23
6 | P1RS001 | RM1006 | ACH/PDC Process | https://drive.google.com/file/d/0ByaFA5DUraUDMW9NMVBGVTZEa1k/view?usp=sharing | Phase I | Tracked under Collections and hence removing this entry from the process list. | Signed Off |  |  | 2016-07-14
7 | P1RS001 | RM1007 | Writeoff |  | Phase I | Final version received | Signed Off |  |  | 2016-07-27
8 | P1RS001 | RM1008 | Insurance Process | https://drive.google.com/file/d/0ByaFA5DUraUDS20xT1hxT2YxQXM/view?usp=sharing | Phase I | Attached final process map. | Signed Off | Kinara |  | 2016-08-03
9 | P1RS001 | RM1009 | Finance/Accounting (Tally Integration) | https://drive.google.com/file/d/0ByaFA5DUraUDVGFoSXhqOVNkbkE/view?usp=sharing | Phase I | IRF to send the final Accounting entries document after making changes identified during the discussion with Kinara | Signed Off | IRF |  | 2016-08-02
10 | P1RS001 | RM1010 | Reporting | NA | Phase I | List of Reports along with formats shared by Kinara and will be analyzed by us. We will have a separate discussion on this. | Pending discussion | IRF/Kinara
11 | P1RS001 | RM1011 | Product Definition | https://drive.google.com/file/d/0ByaFA5DUraUDTmc2aGw1Rm5ORm8/view?usp=sharing | Phase I | Sign off given with a condition: For LOC product, fixed percentage will be used in phase I. During Phase II, percentage should be maintained based on amount slab at the product level and derived based on the loan amount. | Signed Off |  |  | 2016-08-01
12 | P1RS001 | RM1012 | NPA |  | Phase I | Final version received | Signed Off |  |  | 2016-07-27
13 | P1RS001 | RM1013 | Restructuring |  | Phase 2 | Final version received | Signed Off |  |  | 2016-07-27
14 | RS002 | RM2001 | Direct Origination |  | Phase II | Draft version received from Roshan. Need to review | Pending Review | IRF
15 | RS002 | RM2002 | LUC and Social Impact |  | Phase II | Initial discussion happened with Kinara and documented. Detailed discussion is pending | Pending discussion | IRF/Kinara
16 | RS002 | RM2003 | Loan Origination |  | Phase II | Loan Origination process document shared with Kinara on 01-Aug-2016 | Pending Review | Kinara
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
[6 empty] | 2016-08-24 | 2016-08-25
[6 empty] | 2016-08-26 | 2016-09-03 |  |  | 1900-01-13
[6 empty] | 2016-08-26 | 2016-09-03 |  |  | 1900-01-13
[6 empty] | 2016-08-29 | 2016-09-03
[6 empty] | 2016-09-05 | 2016-09-28
[6 empty] | 2016-09-29 | 2016-09-29

## ActivityTrackerPhase1
Stage ID | Stage Name | Process ID | Process Name | Activity Description | Responsibility | Expected Start Date | Expected End Date | Activity Start Date | Activity End Date | Planned Effort | Actual Effort | % Completion | Status | Remarks
P1RS001 | Requirements/Process Deep Dive | RM1001 | Loan Booking | Loan Booking: Requirement Study | Krithika | 2016-07-04 | 2016-07-08 | 2016-07-04 | 2016-07-08 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1006 | ACH/PDC Process | ACH/PDC Process: Requirement Study | Krithika | 2016-07-04 | 2016-07-08 | 2016-07-04 | 2016-07-08 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1004 | Collections | Collections: Requirement Study | Krithika | 2016-07-04 | 2016-07-08 | 2016-07-04 | 2016-07-08 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1002 | Document Tracking | Document Tracking: Requirement Study | Krithika | 2016-07-04 | 2016-07-08 | 2016-07-04 | 2016-07-08 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1003 | Inventory Management | Inventory Management: Requirement Study | Krithika | 2016-07-04 | 2016-07-08 | 2016-07-04 | 2016-07-08 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1005 | Customer Notifications | Customer Notifications: Requirement Study | Krithika | 2016-07-04 | 2016-07-08 | 2016-07-04 | 2016-07-08 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1008 | Insurance Process | Insurance Process: Requirement Study | Krithika | 2016-07-04 | 2016-07-08 | 2016-07-04 | 2016-07-08 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1009 | Finance/Accounting (Tally Integration) | Finance/Accounting (Tally Integration): Requirement Study | Karthikeyan | 2016-07-04 | 2016-07-08 | 2016-07-04 | 2016-07-08 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1011 | Product Definition | Product Definition: Requirement Study | Krithika | 2016-06-13 | 2016-06-17 | 2016-06-13 | 2016-06-17 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1007 | Writeoff | Write off: Requirement Study | Karthikeyan | 2016-07-09 | 2016-07-09 | 2016-07-09 | 2016-07-09 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1012 | NPA | NPA: Requirement Study | Karthikeyan | 2016-07-09 | 2016-07-09 | 2016-07-09 | 2016-07-09 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1013 | Restructuring | Restructuring: Requirement Study | Karthikeyan | 2016-07-09 | 2016-07-09 | 2016-07-09 | 2016-07-09 | 2 | 2 | 100% | Completed
P1RS001 | Requirements/Process Deep Dive | RM1010 | Reporting | Reporting: Requirement Study | Amit | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1001 | Loan Booking | Loan Booking: Sign Off | Krithika | 2016-07-18 | 2016-07-18 | 2016-07-18 | 2016-07-18 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1006 | ACH/PDC Process | ACH/PDC Process: Sign Off | Krithika | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1004 | Collections | Collections: Sign Off | Krithika | 2016-07-18 | 2016-07-18 | 2016-07-18 | 2016-07-18 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1002 | Document Tracking | Document Tracking: Sign Off | Krithika | 2016-07-18 | 2016-07-18 | 2016-07-18 | 2016-07-18 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1003 | Inventory Management | Inventory Management: Sign Off | Krithika | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1005 | Customer Notifications | Customer Notifications: Sign Off | Krithika | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1008 | Insurance Process | Insurance Process: Sign Off | Krithika | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1009 | Finance/Accounting (Tally Integration) | Finance/Accounting (Tally Integration): Sign Off | Karthikeyan | 2016-08-02 | 2016-08-02 | 2016-08-02 | 2016-08-02 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1011 | Product Definition | Product Definition: Sign Off | Krithika | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1007 | Writeoff | Write off: Sign Off | Karthikeyan | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1012 | NPA | NPA: Sign Off | Karthikeyan | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1013 | Restructuring | Restructuring: Sign Off | Karthikeyan | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2 | 2 | 100% | Completed
P1RS002 | Requirements Signoff | RM1010 | Reporting | Reporting: Sign Off | Amit | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2 | 2 | 100% | Completed
P1MG001 | Migration Discussion |  |  | Migration Discussion | Karthik | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 1 | 1 | 100% | Completed
P1MG002 | Migration Strategy Document |  |  | Migration Strategy Document Preparation | Karthik | 2016-07-28 | 2016-08-05 | 2016-07-28 | 2016-08-05 | 5 | 6 | 100% | Completed
P1CD001 | Customization Delivery | RM1001 | Loan Booking | Loan Booking: Customization Delivery | Karthik | 2016-07-20 | 2016-08-26 | 2016-07-20 |  |  |  |  | WIP
P1CD001 | Customization Delivery | RM1006 | ACH/PDC Process | ACH/PDC Process: Customization Delivery | Karthik | 2016-07-20 | 2016-08-26 | 2016-07-20 |  |  |  |  | WIP
P1CD001 | Customization Delivery | RM1004 | Collections | Collections: Customization Delivery | Karthik | 2016-07-20 | 2016-08-26 | 2016-07-20 |  |  |  |  | WIP
P1CD001 | Customization Delivery | RM1002 | Document Tracking | Document Tracking: Customization Delivery | Karthik | [7 empty] | Pending
P1CD001 | Customization Delivery | RM1003 | Inventory Management | Inventory Management: Customization Delivery | Karthik | [7 empty] | Pending
P1CD001 | Customization Delivery | RM1005 | Customer Notifications | Customer Notifications: Customization Delivery | Karthik | 2016-07-20 | 2016-08-26 | 2016-07-20 |  |  |  |  | WIP
P1CD001 | Customization Delivery | RM1008 | Insurance Process | Insurance Process: Customization Delivery | Karthik | 2016-07-20 | 2016-08-26 | 2016-07-20 |  |  |  |  | WIP
P1CD001 | Customization Delivery | RM1009 | Finance/Accounting (Tally Integration) | Finance/Accounting (Tally Integration): Customization Delivery | Karthik | 2016-07-20 | 2016-08-26 | 2016-07-20 |  |  |  |  | WIP
P1CD001 | Customization Delivery | RM1011 | Product Definition | Product Definition: Customization Delivery | Karthik | 2016-07-20 | 2016-08-26 | 2016-07-20 |  |  |  |  | WIP
P1CD001 | Customization Delivery | RM1007 | Writeoff | Write off: Customization Delivery | Karthik | 2016-07-20 | 2016-08-15 | 2016-07-20 |  |  |  |  | WIP
P1CD001 | Customization Delivery | RM1012 | NPA | NPA: Customization Delivery | Karthik | 2016-07-20 | 2016-08-15 | 2016-07-20 |  |  |  |  | WIP
P1CD001 | Customization Delivery | RM1013 | Restructuring | Restructuring: Customization Delivery | Karthik | [7 empty] | Pending
P1CD001 | Customization Delivery | RM1010 | Reporting | Reporting: Customization Delivery | Amit | [7 empty] | Pending
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design Document: Loan Booking | Krithika | 2016-08-03 | 2016-08-05 | 2016-08-02 | 2016-08-03 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design Document: ACH/PDC | Karthikeyan | 2016-08-05 | 2016-08-05 | 2016-08-03 | 2016-08-05 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1004 | Collections | UI Design Document: Collections | Sarthak | 2016-08-03 | 2016-08-05 | 2016-08-03 | 2016-08-05 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1002 | Document Tracking | UI Design Document: Document Tracking | Krithika | 2016-08-08 | 2016-08-10 | 2016-08-10 | 2016-08-11 | 2 | 2 |  | Completed | For Phase 2
P1UI001 | UI Design Development | RM1003 | Inventory Management | UI Design Document: Inventory Management | Krithika | 2016-08-05 | 2016-08-09 | 2016-08-03 | 2016-08-04 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1008 | Insurance Process | UI Design Document: Insurance Process | Krithika | 2016-08-08 | 2016-08-10 | 2016-08-04 | 2016-08-05 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1007 | Writeoff | UI Design Document: Write Off | Karthikeyan | 2016-08-05 | 2016-08-09 | 2016-08-03 | 2016-08-05 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1012 | NPA | UI Design Document: NPA | Sarthak | 2016-08-03 | 2016-08-05 | 2016-08-03 | 2016-08-05 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1013 | Restructuring | UI Design Document: Restructuring | Karthikeyan | 2016-08-05 | 2016-08-05 | 2016-08-05 |  | 2 |  |  | WIP | For Phase 2
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design Document Review: Loan Booking | Karthik | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-12 | 1 |  |  | Completed
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design Document Review: ACH/PDC | Karthik | 2016-08-10 | 2016-08-10 | 2016-08-10 |  | 1 |  |  | WIP
P1UI001 | UI Design Development | RM1004 | Collections | UI Design Document Review: Collections | Karthik | 2016-08-10 | 2016-08-10 | 2016-08-10 |  | 1 |  |  | WIP
P1UI001 | UI Design Development | RM1002 | Document Tracking | UI Design Document Review: Document Tracking | Karthik | 2016-08-10 | 2016-08-10 |  |  | 1 |  |  | Pending
P1UI001 | UI Design Development | RM1003 | Inventory Management | UI Design Document Review: Inventory Management | Karthik | 2016-08-11 | 2016-08-11 |  |  | 1 |  |  | Pending
P1UI001 | UI Design Development | RM1008 | Insurance Process | UI Design Document Review: Insurance Process | Karthik | 2016-08-11 | 2016-08-11 |  |  | 1 |  |  | Pending
P1UI001 | UI Design Development | RM1007 | Writeoff | UI Design Document Review: Write Off | Karthik | 2016-08-11 | 2016-08-11 |  |  | 1 |  |  | Pending
P1UI001 | UI Design Development | RM1012 | NPA | UI Design Document Review: NPA | Karthik | 2016-08-11 | 2016-08-11 |  |  | 1 |  |  | Pending
P1UI001 | UI Design Development | RM1013 | Restructuring | UI Design Document Review: Restructuring | Karthik | 2016-08-11 | 2016-08-11 |  |  | 1 |  |  | Pending
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Pending for Loan Booking Queue | Suraj | 2016-08-03 | 2016-08-05 | 2016-07-12 | 2016-07-20 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Capture Disbursement Details | Suraj | 2016-08-03 | 2016-08-05 | 2016-08-03 | 2016-08-04 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Document Generation and Upload Queue | Suraj | 2016-08-03 | 2016-08-05 | 2016-07-12 | 2016-07-20 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Pending for Document Verification Queue | Suraj | 2016-08-03 | 2016-08-05 | 2016-08-03 | 2016-08-04 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Verify Documents | Suraj | 2016-08-03 | 2016-08-05 | 2016-07-12 | 2016-07-20 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Rejected Disbursements Queue | Suraj | 2016-08-03 | 2016-08-05 | 2016-08-03 | 2016-08-16 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Ready for Disbursement Queue | Suraj | 2016-08-03 | 2016-08-05 | 2016-08-03 | 2016-08-04 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Disbursement | Suraj | 2016-08-03 | 2016-08-05 | 2016-08-03 | 2016-08-04 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Pending for Disbursement Confirmation Queue | Suraj | 2016-08-03 | 2016-08-05 | 2016-08-03 | 2016-08-04 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Update Confirmation status | Suraj | 2016-08-03 | 2016-08-05 | 2016-08-03 | 2016-08-04 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Rejected Disbursement Queue | Suraj | 2016-08-03 | 2016-08-05 | 2016-08-03 | 2016-08-05 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Multi Tranche Disbursement Queue | Suraj | 2016-08-12 | 2016-08-15 | 2016-08-16 | 2016-08-16 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Multi Tranche Disbursment Details Screen | Suraj | 2016-08-12 | 2016-08-15 | 2016-08-16 | 2016-08-16 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : FRO Approval Queue | Suraj | 2016-08-16 | 2016-08-17 | 2016-08-16 | 2016-08-16 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : FRO Approval Screen | Suraj | 2016-08-16 | 2016-08-17 | 2016-08-16 | 2016-08-16 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : CRO Approval Queue | Suraj | 2016-08-16 | 2016-08-17 | 2016-08-16 | 2016-08-16 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : CRO Approval Screen | Suraj | 2016-08-16 | 2016-08-17 | 2016-08-16 | 2016-08-16 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Schedule Generation Queue | Suraj | 2016-08-18 | 2016-08-18 | 2016-08-16 | 2016-08-16 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Update Account Details Screen | Suraj | 2016-08-18 | 2016-08-18 | 2016-08-16 | 2016-08-16 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH/ PDC Registartion | Kaushik | 2016-08-05 | 2016-08-08 | 2016-08-18 | 2016-08-18 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH Submission | Suraj | 2016-08-05 | 2016-08-08 | 2016-08-05 | 2016-08-08 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH Status update | Suraj | 2016-08-05 | 2016-08-08 | 2016-08-05 | 2016-08-08 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH clearing | Suraj | 2016-08-08 | 2016-08-09 | 2016-08-05 | 2016-08-08 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH/ PDC Repayment - Upload/ Rejection screen | Suraj | 2016-08-08 | 2016-08-09 |  |  | 2 |  |  | Pending
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :PDC status update screen | Suraj | 2016-08-08 | 2016-08-09 |  |  | 2 |  |  | Pending
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Bounce Queue | Karthik | 2016-08-08 | 2016-08-09 | 2016-08-08 | 2016-08-09 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :P2P Update | Karthik | 2016-08-08 | 2016-08-09 | 2016-08-08 | 2016-08-09 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Collect Payment | Karthik | 2016-08-08 | 2016-08-09 | 2016-08-08 | 2016-08-09 | 2 |  |  | Completed
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Credit Validation | Karthik | 2016-08-10 | 2016-08-11 | 2016-08-18 | 2016-08-18 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Transaction Authorization Queue | Karthik | 2016-08-10 | 2016-08-11 | 2016-08-18 | 2016-08-18 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Transaction Authorization Screen | Karthik | 2016-08-10 | 2016-08-11 | 2016-08-18 | 2016-08-18 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Bounce Queue for Hub Manager | Karthik | 2016-08-12 | 2016-08-13 | 2016-08-16 | 2016-08-16 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Bounce Queue for Recovery Agent | Karthik | 2016-08-12 | 2016-08-13 | 2016-08-16 | 2016-08-16 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Deposit Stage Queue - Cash Payment | Karthik | 2016-08-12 | 2016-08-13 | 2016-08-18 | 2016-08-18 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1004 | Collections | UI Design Deposit stage Screen | Karthik | 2016-08-12 | 2016-08-13 | 2016-08-18 | 2016-08-18 | 2 | 2 |  | Completed
P1UI001 | UI Design Development | RM1007 | Writeoff | UI Design :Write Off Queue | Suraj | 2016-08-10 | 2016-08-11 |  |  | 2 |  |  | Pending
P1UI001 | UI Design Development | RM1013 | Restructuring | UI Design :Restructuring Screen | Suraj | 2016-08-10 | 2016-08-11 |  |  | 2 |  |  | Pending
P1UI001 | UI Design Development | RM1013 | Restructuring | UI Design :Restructuring Approval - Level 1 | Suraj | 2016-08-10 | 2016-08-11 |  |  | 2 |  |  | Pending
P1UI001 | UI Design Development | RM1013 | Restructuring | UI Design :Restructuring Approval - Level 2 | Suraj | 2016-08-12 | 2016-08-13 |  |  | 2 |  |  | Pending
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Basic Entity Enrolmment | Shahal | 2016-08-16 | 2016-08-25 |  |  | 1
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Loan input screen | Shahal | 2016-08-16 | 2016-08-25 |  |  | 3
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Pending for Loan Booking Queue | Shahal | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Capture Disbursement Details | Shahal | 2016-08-16 | 2016-08-25 |  |  | 1.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Document Generation and Upload Queue | Shahal | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Pending for Document Verification Queue | Shahal | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Verify Documents | Shahal | 2016-08-16 | 2016-08-25 |  |  | 1.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Rejected Documents Queue | Shahal | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Ready for Disbursement Queue | Shahal | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Disbursement | Shahal | 2016-08-16 | 2016-08-25 |  |  | 1.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Pending for Disbursement Confirmation Queue | Shahal | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Update Confirmation status | Shahal | 2016-08-16 | 2016-08-25 |  |  | 1.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Rejected Disbursement Queue | Shahal | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH/ PDC Registartion | Suraj | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH Submission | Suraj | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH Status update | Suraj | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH clearing | Suraj | 2016-08-16 | 2016-08-25 |  |  | 1.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH/ PDC Repaymnet - Upload/ Rejection screen | Suraj | 2016-08-16 | 2016-08-25 |  |  | 1.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :PDC status update screen | Suraj | 2016-08-16 | 2016-08-25 |  |  | 1.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Bounce Queue | Karthik | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :P2P Update | Karthik | 2016-08-16 | 2016-08-25 |  |  | 1 |  |  | Pending
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Overdue collection update | Karthik | 2016-08-16 | 2016-08-25 |  |  | 1 |  |  | Pending
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Credit Validation | Karthik | 2016-08-16 | 2016-08-25 |  |  | 1 |  |  | Pending
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Transaction Authorization Queue | Karthik | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Transaction Authorization Screen | Karthik | 2016-08-16 | 2016-08-25 |  |  | 1.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Bounce Queue for Hub Manager | Karthik | 2016-08-16 | 2016-08-25 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Bounce Queue for Recovery Agent | Karthik | 2016-09-13 | 2016-09-20 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Deposit Stage Queue - Cash Payment | Karthik | 2016-09-13 | 2016-09-20 |  |  | 1 |  |  | Pending
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Cash Deposit Confirmation Queue | Karthik | 2016-09-13 | 2016-09-20 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1007 | Writeoff | UI Integration with Service :Write Off Queue | Suraj | 2016-09-13 | 2016-09-20 |  |  | 0.5 |  |  | Pending
P1CD002 | UI Integration with Services | RM1013 | Restructuring | UI Integration with Service :Restructuring Screen | Suraj | 2016-09-13 | 2016-09-20 |  |  | 1 |  |  | Pending
P1CD002 | UI Integration with Services | RM1013 | Restructuring | UI Integration with Service :Restructuring Approval - Level 1 | Suraj | 2016-09-13 | 2016-09-20 |  |  | 1 |  |  | Pending
P1CD002 | UI Integration with Services | RM1013 | Restructuring | UI Integration with Service :Restructuring Approval - Level 2 | Suraj | 2016-09-13 | 2016-09-20 |  |  | 1 |  |  | Pending
P1TP001 | Test Plan Delivery |  |  | Test Plan Communication | Karthik | 2016-08-08 | 2016-08-08 |  |  | 1 |  |  | Pending
P1TP001 | Test Plan Delivery |  |  | Test Plan Preparation | Swapnil | 2016-08-16 | 2016-08-25 |  |  | 8 |  |  | Pending
P1TP001 | Test Plan Delivery |  |  | Test Plan Sign off | Swapnil | 2016-08-26 | 2016-08-27 |  |  | 2 |  |  | Pending
P1MG003 | Migration Strategy Document Sign off |  |  | Migration Strategy Document Sign Off | Karthik | 2016-08-04 | 2016-08-12 |  |  | 7 |  |  | Pending
P1MG004 | Migration Script Preparation |  |  | Migration Script generation | Karthikeyan | 2016-08-16 | 2016-08-20 |  |  | 5 |  |  | Pending
P1SIT001 | System Integration Testing |  |  | SIT Environment Preparation | Ajay | 2016-08-24 | 2016-08-25 |  |  | 2 |  |  | Pending
P1SIT001 | System Integration Testing |  |  | SIT Execution | Krithika, Karthikeyan | 2016-08-26 | 2016-09-03 |  |  | 14 |  |  | Pending
P1SIT001 | System Integration Testing |  |  | SIT Support | Karthik, Suraj, Shahal, Stalin | 2016-08-26 | 2016-09-03 |  |  | 14 |  |  | Pending
P1UT001 | User Training |  |  | User Training - Kinara | Dhivya | 2016-08-29 | 2016-09-03 |  |  | 6 |  |  | Pending
P1UAT001 | UAT Setup |  |  | UAT Environment Setup | Ajay | 2016-08-26 | 2016-08-27 |  |  | 2 |  |  | Pending
P1MG005 | Migration Testing Round 1 |  |  | Migration Round 1 Environment Setup | Ajay | 2016-08-28 | 2016-08-29 |  |  | 2 |  |  | Pending
P1MG005 | Migration Testing Round 1 |  |  | Migration Testing & Support Round 1 | Karthikeyan | 2016-08-30 | 2016-09-02 |  |  | 4 |  |  | Pending
P1MG005 | Migration Testing Round 1 |  |  | Migration Round 2 Environment Refresh | Ajay | 2016-09-03 | 2016-09-04 |  |  | 2 |  |  | Pending
P1MG005 | Migration Testing Round 1 |  |  | Migration Testing & Support Round 1 | Karthikeyan | 2016-09-05 | 2016-09-09 |  |  | 5 |  |  | Pending
P1MG007 | Migration Sign off |  |  | Migration Sign Off | Karthikeyan | 2016-09-12 | 2016-09-13 |  |  | 2 |  |  | Pending
P1MP009 | User Acceptance Testing |  |  | UAT Support | Karthik, Suraj, Shahal, Stalin | 2016-09-05 | 2016-09-28 |  |  | 60 |  |  | Pending
P1MP010 | UAT Sign off |  |  | UAT Sign Off | Karthik | 2016-09-29 | 2016-09-29 |  |  | 1 |  |  | Pending
P1MP012 | Post Live -Onsite support |  |  | On Site Support | Krithika, Karthikeyan | 2016-10-03 | 2016-10-15 |  |  | 20 |  |  | Pending
P1CD001 | Customization Delivery |  |  | ACH Batch file format | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Covering letter format for ACH Batch processing | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | ACH Response file format | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | PDC demand excel format | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | PDC bounced cases format | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Loan Application format | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Legal Agreement | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Legal Schedule | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Loan Sanction Document | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | PHS | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Other Supporting documents | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Insurance Feed file format | Amit | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Sales pipeline | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Target vs achieved | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Stagewise TAT | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Portfolio Collection Report | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | MSDF Ops Data | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | PAR Report | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | ALM Asset side | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Fund Allocation | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | IRR Calculation | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | IIR Calculation | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | LTV details | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Expected Demand & Actual Demand | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Regionwise POS | Balakrishnan | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | AUM Management | Kaushik | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Portfolio Report for MAS | Kaushik | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Write off cases details | Kaushik | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Run Down Report | Kaushik | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Net NAP Calculation | Kaushik | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | MAS Monthly Report | Kaushik | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | MAS Loan Report | Kaushik | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | Caspian Quarterly Report | Kaushik | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | IFMR Quaretly Report | Kaushik | [7 empty] | Pending
P1CD001 | Customization Delivery |  |  | PAR Provision Calculation | Kaushik | [7 empty] | Pending
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design Document Rework: Loan Booking | Karthik | 2016-08-12 | 2016-08-17 | 2016-08-12 |  |  |  |  | WIP
P1SIT002 | SIT Test Plan | RM1001 | Loan Booking | SIT Test Plan Preparation: Loan Booking | Krithika | 2016-08-18 | 2016-08-19 |  |  | 2 |  |  | Pending
P1SIT002 | SIT Test Plan | RM1004 | Collections | SIT Test Plan Preparation: Collections | Krithika | 2016-08-22 | 2016-08-23 |  |  | 2 |  |  | Pending
P1SIT002 | SIT Test Plan | RM1005 | Customer Notifications | SIT Test Plan Preparation: Customer Notification | Krithika | 2016-08-24 | 2016-08-25 |  |  | 2 |  |  | Pending
P1SIT002 | SIT Test Plan | RM1008 | Insurance Process | SIT Test Plan Preparation: Insurance Process | Krithika | 2016-08-26 | 2016-08-26 |  |  | 1 |  |  | Pending
P1SIT002 | SIT Test Plan | RM1006 | ACH/PDC Process | SIT Test Plan Preparation: ACH/PDC | Karthikeyan | 2016-08-19 | 2016-08-22 |  |  | 2 |  |  | Pending
P1SIT002 | SIT Test Plan | RM1007 | Writeoff | SIT Test Plan Preparation: Write Off | Karthikeyan | 2016-08-23 | 2016-08-23 |  |  | 1 |  |  | Pending
P1SIT002 | SIT Test Plan | RM1012 | NPA | SIT Test Plan Preparation: NPA | Karthikeyan | 2016-08-24 | 2016-08-24 |  |  | 1 |  |  | Pending
P1SIT002 | SIT Test Plan | RM1009 | Finance/Accounting (Tally Integration) | SIT Test Plan Preparation: Finance/Accounting (Tally Integration) | Karthikeyan | 2016-08-25 | 2016-08-25 |  |  | 1 |  |  | Pending
P1SIT002 | SIT Test Plan | RM1011 | Product Definition | SIT Test Plan Preparation: Product Definition | Karthikeyan | 2016-08-26 | 2016-08-26 |  |  | 1 |  |  | Pending
P1SIT003 | SIT Test Plan Review | RM1001 | Loan Booking | SIT Test Plan Preparation: Loan Booking | Dhivya | 2016-08-22 | 2016-08-22 |  |  | 1 |  |  | Pending
P1SIT003 | SIT Test Plan Review | RM1004 | Collections | SIT Test Plan Preparation: Collections | Dhivya | 2016-08-24 | 2016-08-24 |  |  | 1 |  |  | Pending
P1SIT003 | SIT Test Plan Review | RM1005 | Customer Notifications | SIT Test Plan Preparation: Customer Notification | Rahul | 2016-08-26 | 2016-08-26 |  |  | 1 |  |  | Pending
P1SIT003 | SIT Test Plan Review | RM1008 | Insurance Process | SIT Test Plan Preparation: Insurance Process | Rahul | 2016-08-29 | 2016-08-29 |  |  | 1 |  |  | Pending
P1SIT003 | SIT Test Plan Review | RM1006 | ACH/PDC Process | SIT Test Plan Preparation: ACH/PDC | Dhivya | 2016-08-23 | 2016-08-23 |  |  | 1 |  |  | Pending
P1SIT003 | SIT Test Plan Review | RM1007 | Writeoff | SIT Test Plan Preparation: Write Off | Rahul | 2016-08-24 | 2016-08-24 |  |  | 1 |  |  | Pending
P1SIT003 | SIT Test Plan Review | RM1012 | NPA | SIT Test Plan Preparation: NPA | Dhivya | 2016-08-25 | 2016-08-25 |  |  | 1 |  |  | Pending
P1SIT003 | SIT Test Plan Review | RM1009 | Finance/Accounting (Tally Integration) | SIT Test Plan Preparation: Finance/Accounting (Tally Integration) | Dhivya | 2016-08-26 | 2016-08-26 |  |  | 1 |  |  | Pending
P1SIT003 | SIT Test Plan Review | RM1011 | Product Definition | SIT Test Plan Preparation: Product Definition | Dhivya | 2016-08-29 | 2016-08-29 |  |  | 1 |  |  | Pending

## Legend
Types of Gantt
Planned
Actual
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
2016-08-25
| 2016-08-24 | 2016-08-25
| 2016-08-26 | 2016-09-03 | 14
| 2016-08-26 | 2016-09-03 | 14
| 2016-08-29 | 2016-09-03
| 2016-09-05 | 2016-09-28
| 2016-09-29 | 2016-09-29

## Screen_dev_Breakup
Stage ID | Stage Name | Process ID | Process Name | Activity Description | Responsibility | Expected Start Date | Expected End Date | Activity Start Date | Activity End Date
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Pending for Loan Booking Queue | Suraj | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Capture Disbursement Details | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Document Generation and Upload Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Pending for Document Verification Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Verify Documents | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Rejected Disbursements Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Ready for Disbursement Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Disbursement | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Pending for Disbursement Confirmation Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Update Confirmation status | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Rejected Disbursement Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Multi Tranche Disbursement Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Multi Tranche Disbursment Details Screen | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : FRO Approval Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : FRO Approval Screen | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : CRO Approval Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : CRO Approval Screen | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Schedule Generation Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Update Account Details Screen | Suraj
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH/ PDC Registartion | Kaushik
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH Submission | Suraj
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH Status update | Suraj
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH clearing | Suraj
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH/ PDC Repayment - Upload/ Rejection screen | Suraj
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :PDC status update screen | Suraj
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Bounce Queue | Karthik
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :P2P Update | Karthik
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Collect Payment | Karthik
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Credit Validation | Karthik
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Transaction Authorization Queue | Karthik
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Transaction Authorization Screen | Karthik
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Bounce Queue for Hub Manager | Karthik
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Bounce Queue for Recovery Agent | Karthik
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Deposit Stage Queue - Cash Payment | Karthik
P1UI001 | UI Design Development | RM1004 | Collections | UI Design Deposit stage Screen | Karthik
P1UI001 | UI Design Development | RM1007 | Writeoff | UI Design :Write Off Queue | Suraj
P1UI001 | UI Design Development | RM1013 | Restructuring | UI Design :Restructuring Screen | Suraj
P1UI001 | UI Design Development | RM1013 | Restructuring | UI Design :Restructuring Approval - Level 1 | Suraj
P1UI001 | UI Design Development | RM1013 | Restructuring | UI Design :Restructuring Approval - Level 2 | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Integration with Service : Basic Entity Enrolmment | Shahal
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Integration with Service : Loan input screen | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Pending for Loan Booking Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Capture Disbursement Details | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Document Generation and Upload Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Pending for Document Verification Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Verify Documents | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Rejected Documents Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Ready for Disbursement Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Disbursement | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Pending for Disbursement Confirmation Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Update Confirmation status | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Rejected Disbursement Queue | Shahal
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH/ PDC Registartion | Suraj
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH Submission | Suraj
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH Status update | Suraj
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH clearing | Suraj
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH/ PDC Repaymnet - Upload/ Rejection screen | Suraj
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :PDC status update screen | Suraj
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Bounce Queue | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :P2P Update | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Overdue collection update | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Credit Validation | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Transaction Authorization Queue | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Transaction Authorization Screen | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Bounce Queue for Hub Manager | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Bounce Queue for Recovery Agent | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Deposit Stage Queue - Cash Payment | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Cash Deposit Confirmation Queue | Karthik
P1CD002 | UI Integration with Services | RM1007 | Writeoff | UI Integration with Service :Write Off Queue | Suraj
P1CD002 | UI Integration with Services | RM1013 | Restructuring | UI Integration with Service :Restructuring Screen | Suraj
P1CD002 | UI Integration with Services | RM1013 | Restructuring | UI Integration with Service :Restructuring Approval - Level 1 | Suraj
P1CD002 | UI Integration with Services | RM1013 | Restructuring | UI Integration with Service :Restructuring Approval - Level 2 | Suraj
Note on E2: Madhusudhanan S ¦ IFMR Rural Finance: UI Design 1) Translation 2) Label code -field mapping 3) Page flow(routing post action) 4) Mandatory 5) Data type 6) LOV-ENUM 7) page naming 8) Validations

## dev
Stage ID | Stage Name | Process ID | Process Name | Activity Description | Responsibility | Filename | Pagename | Expected Start Date | Expected End Date | Activity Start Date | Activity End Date
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Pending for Loan Booking Queue | Suraj | loans/individual/booking/PendingQueue.js | loans.individual.booking.PendingQueue | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Capture Disbursement Details | Suraj |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Document Generation and Upload Queue | Suraj |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Pending for Document Verification Queue | Suraj |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Verify Documents | Suraj |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Rejected Disbursements Queue | Suraj |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Ready for Disbursement Queue | Suraj |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Disbursement | Suraj |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Pending for Disbursement Confirmation Queue | Suraj |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Update Confirmation status | Suraj |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Rejected Disbursement Queue | Suraj |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Multi Tranche Disbursement Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Multi Tranche Disbursment Details Screen | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : FRO Approval Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : FRO Approval Screen | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : CRO Approval Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : CRO Approval Screen | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Schedule Generation Queue | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Design : Update Account Details Screen | Suraj
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH/ PDC Registartion | Suraj
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH Submission | Suraj
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH Status update | Suraj
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH clearing | Suraj
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :ACH/ PDC Repayment - Upload/ Rejection screen | Suraj
P1UI001 | UI Design Development | RM1006 | ACH/PDC Process | UI Design :PDC status update screen | Suraj
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Bounce Queue | Kaushik |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :P2P Update | Kaushik |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Collect Payment | Kaushik |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Credit Validation | Kaushik |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Transaction Authorization Queue | Kaushik |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Transaction Authorization Screen | Sarthak |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Bounce Queue for Hub Manager | Sarthak |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Bounce Queue for Recovery Agent | Sarthak |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1004 | Collections | UI Design :Deposit Stage Queue - Cash Payment | Sarthak |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1004 | Collections | UI Design Deposit stage Screen | Sarthak |  |  | 2016-08-19 | 2016-08-19
P1UI001 | UI Design Development | RM1007 | Writeoff | UI Design :Write Off Queue | Suraj
P1UI001 | UI Design Development | RM1013 | Restructuring | UI Design :Restructuring Screen | Suraj
P1UI001 | UI Design Development | RM1013 | Restructuring | UI Design :Restructuring Approval - Level 1 | Suraj
P1UI001 | UI Design Development | RM1013 | Restructuring | UI Design :Restructuring Approval - Level 2 | Suraj
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Integration with Service : Basic Entity Enrolmment | Shahal
P1UI001 | UI Design Development | RM1001 | Loan Booking | UI Integration with Service : Loan input screen | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Pending for Loan Booking Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Capture Disbursement Details | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Document Generation and Upload Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Pending for Document Verification Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Verify Documents | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Rejected Documents Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Ready for Disbursement Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Disbursement | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Pending for Disbursement Confirmation Queue | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Update Confirmation status | Shahal
P1CD002 | UI Integration with Services | RM1001 | Loan Booking | UI Integration with Service : Rejected Disbursement Queue | Shahal
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH/ PDC Registartion | Suraj
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH Submission | Suraj
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH Status update | Suraj
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH clearing | Suraj
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :ACH/ PDC Repaymnet - Upload/ Rejection screen | Suraj
P1CD002 | UI Integration with Services | RM1006 | ACH/PDC Process | UI Integration with Service :PDC status update screen | Suraj
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Bounce Queue | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :P2P Update | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Overdue collection update | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Credit Validation | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Transaction Authorization Queue | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Transaction Authorization Screen | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Bounce Queue for Hub Manager | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Bounce Queue for Recovery Agent | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Deposit Stage Queue - Cash Payment | Karthik
P1CD002 | UI Integration with Services | RM1004 | Collections | UI Integration with Service :Cash Deposit Confirmation Queue | Karthik
P1CD002 | UI Integration with Services | RM1007 | Writeoff | UI Integration with Service :Write Off Queue | Suraj
P1CD002 | UI Integration with Services | RM1013 | Restructuring | UI Integration with Service :Restructuring Screen | Suraj
P1CD002 | UI Integration with Services | RM1013 | Restructuring | UI Integration with Service :Restructuring Approval - Level 1 | Suraj
P1CD002 | UI Integration with Services | RM1013 | Restructuring | UI Integration with Service :Restructuring Approval - Level 2 | Suraj